## Sheet1
[15 empty] | Visit MM? | Updates Presentations |  | Spring Break | [5 empty] | Senior Design Day - 5/1 | Final Report
Week of: | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16 |  | Week of: | 2020-01-20 | 2020-01-27 | 2020-02-03 | 2020-02-10 | 2020-02-17 | 2020-02-24 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04
[8 empty] | Specific | Update Team Contract, Update Gantt Chart, Submit DMD Paper | bar: 2020-01-20; 2020-03-16
Select Materials/ Components for Replica Catheter | [7 empty] | Measurable | Decide on a Specific Catherter Procedure | bar: 2020-01-20 to 2020-01-27; 2020-03-16
Equations for Angle Readout | [7 empty] | Attainable | Select Materials/ Components for Replica Catheter | bar: 2020-01-20 to 2020-01-27; 2020-03-16
Arduino Code for Motors | [7 empty] | Relevant | Solid Model of all components | bar: 2020-01-20 to 2020-02-03; 2020-03-16
Build Single Wire Proof of Concept | [7 empty] | Time-Based | Get PCBs | bar: 2020-01-27 to 2020-02-10; 2020-03-02 to 2020-03-23
Multi-wire Proof of Concept | [8 empty] | Manufacture Prototype Parts (catheter handle, spools, etc.) | bar: 2020-03-02 to 2020-03-16
Present Functional Prototype | [8 empty] | Assemble Prototype | bar: 2020-03-09 to 2020-03-23
ISO and FDA Standards for Design | [8 empty] | Test for Angle Readout Equations | bar: 2020-03-16; 2020-03-30
Test and Redesign Prototype | bar: 2020-03-16 to 2020-05-04
ISO and FDA Standards for Design
Week of: | 2019-12-02 | 2019-12-09 | 2019-12-16
Motor Arduino Control
Prototype Housing
Lumen/Sheath Manufacturing
Motors Attached to Housing
Multi-wire Proof of Concept
Present Functional Prototype
ISO and FDA Standards for Design